## Sheet1
Summary Progress Report
Lead Local Authority | Bromsgrove District Council | Reporting Period Ending | 2023-12-31
URN | UKSPF-614 E Bromsgrove
Priority | Spend to date | Forecast spend by end of financial year | Note on expected spend
Communities & Place | 279494 | 374808 | Underspend
Supporting Local Business | 359776 | 359776 | Underspend
People & Skills | 39225 | 39225 | On track
Administration | 27808 | 42506 | Underspend
Delivery RAG: Green: On time, in budget & no significant threat to delivery Green/Amber: Success probable Amber: Needs active management attention Amber/Red: Success in doubt R: Success appears unachievable |  | Note on Trend
Communities & Place | G/A | Unchanged
Supporting Local Business | G/A | Unchanged
People & Skills | G | Unchanged
Progress Summary
We are forecasting an underspend of £129,180 for the year 2023/24. This funding will be carried forward to 2024/25. Most of this funding is allocated to projects but expenditure is not expected to be completed by year end due to contractor delays and the grant claim processes. £23,507 of 2023/24 funding has not yet been allocated. A number of potential projects, that reflect the Council's emerging priorities, have been identified and proposals are being developed for the 2023/24 and 2024/24 underspend.
Year end financial forecast
Expected Spend (Capital) | 283166 | Current Underspend (Capital) | 0
Expected Spend (Revenue) | 533149 | Current Underspend (Revenue) | 129180