## Expenditure
Summary Progress Report
Lead Local Authority | Bromsgrove District Council | Reporting Period | 2023/24
URN | UKSPF-614 E Bromsgrove
Priority | Spend to date | Spend at end of financial year | Note on expected spend
Communities & Place | 361691 | 361691 | Underspend
Supporting Local Business | 359776 | 359776 | Underspend
People & Skills | 65375 | 65375 | On track
Administration | 41846 | 41846 | Underspend
Delivery RAG: Green: On time, in budget & no significant threat to delivery Green/Amber: Success probable Amber: Needs active management attention Amber/Red: Success in doubt R: Success appears unachievable |  | Note on Trend
Communities & Place |  | Unchanged
Supporting Local Business |  | Unchanged
People & Skills |  | Unchanged
Progress Summary
This report relates to expenditure for the peroid 1/4/23 to 31/3/24. The UKSPF funding for 2023/24 was £944,645 made up of £680,998 2023/24 annual allocation plus £263,647 underspend from 2022/23. Total expenditure for the year was £828,688. The underspend of £115,957 will be carried forward to 2024/25. As we have achieved the 80% spend threshold, we will receive the full 2024/25 allocation at the beginning of the year (expected to be early July). UKSPF funding for 2024/25 is £1,900,172 made up of £1,784,215 annual allocation and £115,957 underspend from 2023/24. 91% of this funding has been committed to projects. Proposals for the remaining 9% (£169,902) are being developed and will be subject to the usual assessment / approval process. The majority of the non-committed funding has been allocated to the People & Skills investment priority. The focus of UKSPF funding in 2023/24 has been on Community & Place projects. The Act on Energy project is performing particularly well, having exceeded a number of its contracted outputs and outcomes. The majority of business support programmes were launched in the second half of the year and although limited outputs and outcomes have been achieved to date, there is a strong pipeline of participants in the support programmes and applications for grants. 2024/25 will see the launch of the People & Skills programmes although some outputs and outcomes are already being achieved within this investment priority by the Volunteer Centre and Volunteer It Yourself.
Year end financial
Capital Spend | 273314 | Underspend (Capital) | 0
Revenue Spend | 555374 | Underspend (Revenue) | 115957

## Deliverables
COMMUNITY & PLACE OUTPUTS
Measure | Unit of Measurement | Contracted | Actual to Date
Amount of green or blue space created or improved | Square metres | 179697 | 29327
Amount of low or zero carbon energy infrastructure completed | Square metres | 2002
Amount of public realm created or improved | Square metres | 16779 | 16879
Number of amenities/facilities created or improved | Number | 13 | 3
Number of events/participatory programmes | Number | 14
Number of households receiving support | Number | 300 | 492
Number of households supported to take energy efficiency measures | Number | 150 | 492
Number of local events or activities supported | Number | 255 | 138
Number of low or zero carbon energy infrastructure installed | Number of units | 41 | 24
Number of neighbourhood improvements undertaken | Number | 22 | 12
Number of new or improved cycleways or foot paths | Number | 5 | 3
Number of organisations receiving grants | Number | 34 | 9
Number of organisations receiving non-financial support | Number | 130 | 129
Number of people attending training sessions | Number | 273 | 309
Number of people reached | Number | 732 | 1139
Number of projects successfully completed | Number | 67 | 2
Number of properties better protected from flooding and coastal erosion | Number | 1
Number of Tourism, Culture or heritage assets created or improved | Number | 2
Number of tournaments supported | Number | 10 | 4
Number of volunteering opportunities supported | Number | 924 | 443
Total length of new or improved cycleways or paths | Kilometres | 0.209 | 0.209
COMMUNITY & PLACE OUTCOMES
Measure | Unit of Measurement | Contracted | Actual to Date
Estimated Carbon Dioxide equivalent reductions as a result of support | Tonnes of CO2e | 1624 | 6514
Improved engagement numbers | Number of people | 523 | 472
Improved perceived/experienced accessibility | Number of people | 50
Improved perception of events | Number of people | 200
Improved perception of facilities/amenities | Number of people | 436 | 90
Improved perception of facility/infrastructure project | Number of people | 2234 | 2034
Improved perception of safety | Number of people | 50
Increased affordability of events/entry |  | 3550
Increased footfall | Number of people | 5480 | 5150
Increased number of properties better protected from flooding and coastal erosion | Number of properties | 1
Increased take up of energy efficiency measures | Number of households | 150 | 84
Increased use of cycleways or foot paths | Number of cyclists or pedestrians | 100 | 100
Increased users of facilities/amenitities | Number of users | 1090 | 40
Increased visitor numbers | Number of people | 4260 | 2000
Jobs created as a result of support | FTE | 1.5 | 1.5
Neighbourhood crimes | Number of crimes | 4 | 4
Number of community-led arts, cultural, heritage and creative programmes as a result of support | Number of programmes | 22
Number of vacant units filled | Number of units | 1
Number of volunteering opportunities created as a result of support | Number of volunteering roles created | 214 | 56
SUPPORTING LOCAL BUSINESS OUTPUTS
Measure | Unit of Measurement | Contracted | Actual to Date
Number of decarbonisation plans developed as a result of support | Number of … | 21 | 6
Number of enterprises receiving grants | Number of … | 33 | 3
Number of enterprises receiving non-financial support | Number of … | 355 | 224
Number of local events or activities supported | Number of … | 2 | 1
Number of people reached | Number of … | 500 | 51525
Number of potential entrepreneurs assisted to be enterprise ready | Number of … | 24 | 15
SUPPORTING LOCAL BUSINESS OUTCOMES
Measure | Unit of Measurement | Contracted | Actual to Date
Estimated Carbon Dioxide equivalent reductions as a result of support | Tonnes of CO2e | 65
Inceased amount of investment | £ | 397500 | 10666.56
Increased number of enterprises supported | Number of … | 110 | 66
Increased visitor numbers | Number of … | 100
Jobs created as a result of support | Number of … | 26 | 15
Jobs safeguarded as a result of support | Number of … | 50 | 7
Number of enterprises adopting new or improved products or services | Number of … | 6 | 1
Number of enterprises adopting new to the firm technologies or processes (numerical value) | Number of … | 18 | 2
Number of enterprises engaged in new markets | Number of … | 7 | 3
Number of enterprises with improved productivity | Number of … | 11 | 1
Number of new enterprises created following support | Number of … | 10 | 2
Number of new to market products | Number of … | 1
Number of vacant units filled | Number of … | 4
PEOPLE & SKILLS OUTPUTS
Measure | Unit of Measurement | Contracted | Actual to Date
Number of economically inactive people engaging with keyworker support services | Number of … | 225 | 21
Number of economically inactive people supported to engage with the benefits system | Number of … | 87
Number of effective engagements between keyworkers and additional services | Number of … | 260
Number of people accessing mental and physical health support leading to employment | Number of … | 89
Number of people attending training sessions | Number of … | 110
Number of people in employment engaging with the skills system | Number of … | 25
Number of people receiving support to gain a vocational licence | Number of … | 17
Number of people receiving support to gain employment | Number of … | 245 | 36
Number of people receiving support to sustain employment | Number of … | 110
Number of people retraining | Number of … | 20
Number of people supported onto a course through provision of financial support | Number of … | 160
Number of people supported to access basic skills courses | Number of … | 238
Number of people supported to engage in job-searching | Number of … | 305
Number of people supported to engage in life skills | Number of … | 187 | 36
Number of people supported to gain a qualification | Number of … | 217 | 17
Number of people supported to participate in education | Number of … | 377 | 34
Number of people taking part in work experience programmes | Number of … | 239 | 40
Number of socially excluded people accessing support | Number of … | 176
Number of volunteerting opportunities supported | Number of … | 234 | 36
PEOPLE & SKILLS OUTCOMES
Measure | Unit of Measurement | Contracted | Actual to Date
Number of active or sustained participants in community groups as a result of support | Number of … | 58
Number of economically active individuals engaged in mainstream skills education and training | Number of … | 115
Number of economically inactive individuals engaging wit benefits system following support | Number of … | 87
Number of people engaged in job-searching following support | Number of … | 283 | 2
Number of people engaged in life skills support following interventions | Number of … | 60 | 21
Number of people engaging with mainstream healthcare services | Number of … | 70
Number of people experiencing reduced structual barriers into employment and into skills provision | Number of … | 299 | 48
Number of people familiarised with employers' expectations including standards of behaviour in the workplace | Number of … | 280 | 47
Number of people gaining a qualification or completing a course following support | Number of … | 184 | 17
Number of people gaining qualifications, licences and skills | Number of … | 151
Number of people in education/training following support | Number of … | 100 | 2
Number of people in employment, including self-employment, following support | Number of … | 158
Number of people reporting increased employability through development of interpersonal skills funded by UKSPF | Number of … | 307 | 24
Number of people in supported employment |  | 55
Number of people sustaining employment for 6 months | Number of … | 84 | 3
Number of people sustaining engagement with keyworker support and additional services | Number of … | 208
Number of people with basic skills following support | Number of … | 149